## Slide 1
Summer Camps in
Bihar, Uttar Pradesh and Madhya Pradesh
in May-June 2023
EEA Webinar
31st August 2023

## Slide 2
What will I speak about today?
Pratham implemented a Large-Scale Summer Camp (May-June 2023) focusing on improving basic language (Hindi) skills of children moving from Std V to Std VI across 3 states of India.
There are main topics that I will speak about are:
How to measure and report impact on learning levels?
How to monitor on going activities and validate program-generated data at scale?
What technology tools were developed to achieve this?
Summarize key learnings from implementing M&E practices in a large-scale intervention.

## Slide 3
What was CAMaL ka CAMP? | “Catch-up” Camps in summer holidays
For children moving from Std V to Std VI (transition from primary to middle school)
THE PROBLEM:
By April 2022, one continuous post COVID school year was over. But children were still recovering from learning loss brought about by COVID school closures.
All India figures from ASER 2022 showed that
  Only 43% of children in Std V could read simple text fluently, and
  About 50% were still struggling with simple 2-digit subtraction with borrowing.
The roll out of the New Education Policy (NEP) 2020 & NIPUN Bharat (FLN Mission) has led school systems to focus on Std I, II and III.
What about older children? For example, what about children moving from Std V to Std VI going from primary school to middle school. How to help such children with their basic/foundational skills?
THE SOLUTION:
A large scale “catch up” campaigns in summer holidays for helping children through this transition. Youth volunteers as instructors.
Major focus in Bihar, Uttar Pradesh & Madhya Pradesh
This poster was given to each volunteer and was pasted on the wall in every camp.

## Slide 4
How were volunteers mobilized? | Overwhelming support from different stakeholders & variety of platforms to identify volunteers
Uttar Pradesh’s Pink Army (Anganwadi workers who assisted in mobilizing volunteers
*Partner organizations included - state governments, district administrations, different government departments in education and skilling, self-help groups, colleges, high schools and other local level civil society organizations.
Quarter page ads were printed in the leading news papers in Bihar during the mobilization stage
With the help of partner organizations* word spread about the summer camp in their respective networks at the district and sub-district level.
In Bihar and Madhya Pradesh, the Education Dept used government media channels such as social media handles, Radio and newspapers, YouTube channels etc to share and encourage volunteers to participate in the campaign.

## Slide 5
How were volunteers trained? | At different platforms at district & sub-district levels, brief training sessions were held, and material was shared
CAMaL Ka Camp volunteer booklet: Provides details on what and how to do activities and includes stories, letter chart (Barakhadi), assessment tools and data collection formats etc.
‘Digital Readiness’ via a Simple Web-link: A volunteer registered, created his/ her profile, uploaded baseline & endline data. In addition, volunteers were provided opportunity to take quizzes.
Digital Stories: Volunteers received audio stories via WhatsApp daily known as Kahani Train. Each audio story is between 3-4 minutes long. Volunteers used this story to do ‘story based’ activities with children.
Digital Courses: Volunteers were given the First Aid Course via WhatsApp in the last week of the camp.
With the help of Pratham and Govt teams in (BH & MP), batch-wise, short 3-4 hour training sessions were held:
1
2
3
4

## Slide 6
Who were the summer camp volunteers? |Across the 3 states, different types of volunteers implemented the 6-week camp and had varying profiles …
Age Group (completed years) | Data from info uploaded on portal
 | Volunteers
<16 yrs | 15,660
16 to 20 yrs | 1,09,399
21 to 25 yrs | 49,919
26 to 30 yrs | 33,179
31 to 35 yrs | 27,158
>35 yrs | 45,531
Chart: Highest Educational Qualification*
| Overall
Below Class X | 0.035518
Class XI | 0.27111
Class XII | 0.41946
UG | 0.2147
PG or Higher | 0.059214
Overall, male-female split was almost 50-50 but in Bihar & UP, 58% of volunteers were female volunteers.
A typical volunteer was female, age between 16-20 years & studied or is studying in high school.
60% of volunteers were currently studying and 88% had access to a smartphone during the campaign.
Location | % Currently studying
UP | 82%
Bihar | 49%
MP | 55%
Overall | 60%
% Total volunteers who uploaded profile | % Total volunteers who uploaded profile |  | 
 | Male | Female | Volunteers
Overall | 49% | 51% | 280,846
High school

## Slide 7
What was the reach & coverage ?| More than 300,000 volunteers participated in the summer camp activities and worked with 3.4 million children across 3 states
KEY FIGURES | MADHYA PRADESH | UTTAR PRADESH | BIHAR
Districts | 52 | 75 | 38
Blocks | 312 | 741 | 537
Villages/ Communities | 42,106 | 62,884 | 36,383
Volunteers registered* | 83,745 | 113,830 | 104,409
Children tested at baseline** | 920,111 | 1,315,206 | 1,246,413
Children tested at endline** | 900,362 | 1,298,251 | 1,206,842
Pratham team members*** | 144 | 579 | 233
3
States
165
Districts
1,590
Blocks
141,373
Communities/ Villages
301,745
volunteers registered
3.48 million children
tested at baseline
3.40 million children
tested at endline
*While this is the number of volunteers who registered, 95% of such volunteers uploaded baseline and 93% uploaded endline |
**Tested children as per volunteer uploaded data | *** Includes all Pratham teams who had volunteers mapped to them or supported in the program
956
Pratham team members
In total, Rs 2.75 crore i.e., (US$ 334,000) was spent by Pratham for the summer camp. This included print materials, training and travel of the teams.
Govts and other partners incurred their own costs.

## Slide 8
How was impact assessed?| A simple reading assessment tool (ASER tool) was used by the volunteers at baseline and at endline
The reading tool has 5 levels: the highest level is a story Std II level, “para” which has text at Std I level, simple everyday words and letters. Those who are not yet able to recognize letters are called “beginners”
If the child can read the para, s/he is asked to read a story
If the child can read the Story fluently and without too many mistakes, s/he is a Story level child. Otherwise s/he is marked at Para level.
If the child cannot read the para or makes more than 3 mistakes while reading it , s/he is asked to read words.
If the child accurately reads 4 out of 5 words, s/he is retested at para level and either marked at Word or Para level depending what s/he is now able to do.
If the child cannot read 4 out of 5 words correctly, then s/he is asked to read letters.
If the child can easily read 4 out 5 letters she is marked at Letter. If not at Beginner level.
Each child is assessed one-on-one
1
2
3
5
4
6

## Slide 9
How much progress in reading was possible? |Volunteers conducted a baseline at the beginning and endline at the end of the 4-week instructional period
Chart: Progress in Hindi Reading at Different Reading Levels: Data uploaded by volunteers
| Baseline | Endline | Baseline | Endline | Baseline | Endline | Baseline | Endline | Uttar Pradesh | Bihar | Madhya Pradesh | Overall
Beginner | 0.19508 | 0.060005 | 0.19481 | 0.060467 | 0.11021 | 0.038391 | 0.17256 | 0.054454
Letter | 0.36823 | 0.21119 | 0.35385 | 0.13158 | 0.23415 | 0.11765 | 0.32765 | 0.15825
Word | 0.38654 | 0.24969 | 0.41444 | 0.22564 | 0.30851 | 0.22335 | 0.37591 | 0.2342
Std I level text | 0.046532 | 0.24307 | 0.024079 | 0.27593 | 0.26725 | 0.30114 | 0.096823 | 0.27007
Std II level text | 0.0036222 | 0.23604 | 0.012825 | 0.30639 | 0.079876 | 0.31947 | 0.027068 | 0.28303
(24 pp)
(30 pp)
(24 pp)
(25 pp)
Overall, there was a 25-percentage point (pp) improvement in the ability to read at least a Std II level text.
Bihar showcased the highest improvement in reading among the 3 states. Overall, at endline, there was a reduction of 29 pp in children at ‘Letter level or below’ between baseline and endline
A small sample of volunteer camp data was verified via field visits (E.g., ~7% camps had verification visits during the baseline period and 80% children’s learning level in the verification was correct.)
Tested | Baseline | Endline
Uttar Pradesh | 13,15,206 | 12,98,251
Bihar | 12,46,413 | 12,06,842
Madhya Pradesh | 9,20,111 | 9,00,362
Overall | 34,81,730 | 34,05,455

## Slide 10
What were the Quality Control mechanisms? Verification and different forms of monitoring processes were put in place
Assessment Verification
Pratham teams/ partner org., visited volunteers during/ within 5-7 days of baseline & endline to verify the assessment.
Randomly re-testing a sample of children to understand their level and match it with what the volunteer reported.
In case significant difference was found, the verifier would highlight the same with the volunteer and conduct re-testing. In most cases, the correct assessment was updated on the portal.
In-person monitoring visits
Simple monitoring checklist was given to anyone visiting a summer camp class. 1-2 volunteers were visited everyday.
The monitor would check whether the class was running, what was the attendance on the day of the visit and ask some basic questions around the implementation.
The monitor would also check if all relevant formats such as attendance and learning progress sheet/ chart were filled.
Due to the scale of the summer camp and short duration, multiple visits to a volunteer was not possible.
Remote Monitoring Calls
Like the in-person visits, each monitor would call 4-5 volunteers daily to understand more about the volunteers' class.
These calls would usually be in the evening and would be in reference to the previous day’s class by the volunteer
As the call was not based on observation but self reported by the volunteer, the monitoring questions were in the form of ‘quiz-type questions’, so that the monitor could accurately gauge whether expected activities were happening or not.

## Slide 11
What were the outcomes of Quality Control mechanisms? Such processes led to accurate data, large scale was tracked, and course correction could be done
Assessment Verification
~7% of volunteers’ assessment was verified at baseline i.e.; a monitor re-checked the assessment done by the volunteer
In such verification cases, either at baseline or endline, 80% of volunteers’ assessment was reported to be correct (Correct means that at least 80% children tested were marked at the correct level as per the verifier)
In-person monitoring visits
17% volunteers were visited through in-person monitoring at least once
91% of the monitoring visits reported that either the class was going on OR started once the monitor reached
Main reason for class not going on was that it was implemented at a different time than the monitoring visit
85% children were attending camp as seen during visits
At least 90% monitoring visits reported all major components of the camp were implemented (formats, activity, TLM)
Remote Monitoring Calls
23% volunteers were called as part of remote monitoring at least once
79% received the call and over 90% of them mentioned that they were implementing the program, could recall details of Kahani Train, the learning profile of their class and share details of the language learning activities
Only 68% reported that they developed any specific TLM for their classes
The main reason for not conducting the class was that they were unavailable for some personal reason

## Slide 12
How was all this data collected?| A one stop weblink based portal was created for the summer camp known as ‘Sahyogi’ which was a common platform

## Slide 13
What were the major M&E learnings? | Large scale campaigns require simple, quick tools that can be easily understood and used by a diverse audience
Provide easy to understand and administer assessment tools for measuring impact in the hands of the implementor. E.g., ASER Tool for assessing reading
Implementors can be data collectors if they are explained the value of the data they are collecting. E.g., Assessment and activities clearly linked with the goal.
Layering digital tasks such as data collection increased accountability amongst the volunteers and provided volunteers ‘digital readiness’ skills. E.g., More than 300,000 volunteers registered on the weblink and at least 93% of them uploaded BL and EL data which indicated the familiarity and understanding of simple data collection tools.
Simple mechanisms for verification provides confidence in the impact that is reported. E.g., At scale, have basic verification checks, especially around learning assessment, as it provides confidence in the outcomes being reported.
Process monitoring can have different approaches – in person and remote. E.g., ~50,000 in-person monitoring visits made to volunteers and over 65,000 monitoring calls. This helped in the regular tracking of activities which were implemented at scale and support was provided to volunteers.

## Slide 14
Thank you!
For more information: contact:
karthik.menon@Pratham.org
info@pratham.org